## Slide 1
Stakeholder | Role | Power (H/M/L) | Interest (H/M/L) | Notes
Omar Mubarak | Owner | H | L | It’s worth sharing the project charter with him even though he’s not typically involved with day-to-day operations
Deanna Coleman | Director of Operations | H | H | Directly work with project manager
Carter Ward | Executive Chef | H | M | Interest in project but not involved in day-to-day decision-making
Gilly Tyson | General Manager (North Location) | M | H | Directly involved in restaurant operations and work closely with project manager, but less influence than CEO and Director of Operations
Alex Schmidt | General Manager (Downtown Location) | M | H | Directly involved in restaurant operations and work closely with project manager, but less influence than CEO and Director of Operations
Nia Williams | General Manager (Waterfront) | L | L | Waterfront location is not involved in this project
Zane Dutchman | Kitchen Manager (North Location) | L | H | Directly work with tablet with high interest with project, but less influence than General Manager
Larissa Stein | Kitchen Manager (Downtown Location) | L | H | Directly work with tablet with high interest with project, but less influence than General Manager
Seydou Diallo | Restaurant Technology Consultant | M | H | Since this is his first major project and he also excited to see the launch and working together with the project team, so he has more power than kitchen manager and high interest to this project
Stakeholder Analysis

## Slide 2
Keep satisfied (high priority)
Manage closely (high effort)
Monitor (minimum effort)
Show consideration
Power
high
low
med
high
low
Omar
Owner
Drag each stakeholder’s box to the appropriate place on the power-interest grid
Deanna
Director of Operations
Carter
Exec. Chef
Gilly
GM - North
Alex
GM - Downtown
Zane
Kitchen Manager - North
Larissa
Kitchen Manager - Downtown
Seydou
Restaurant Consultant
Interest
med
Nia
General Manager - Waterfront